## OrderService
| Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_order_success | 10 | 29 | 解决准备好模版中的bug
| should_cteate_orderItem_when_create_order | 5 | 32 | order嵌套item，mabatis批量插入数据库
| should_call_price_service_when_create_orderitem | 8 | 13 | 引入MockServer
| should_call_inventory_service_when_create_orderItem | 8 | 12 | Map<String,List<Map>>转json
| should_return_400_when_post_order_fail | 3 | 16 | 调用其他服务失败情况
| should_return_200_when_get_orders_success | 8 | 12
| should_return_200_when_get_order_success | 8 | 10
| shoule_return_404_when_get_order_fail | 3 | 1
| should_return_201_when_post_payment_success | 10 | 19 | Context问题
| should_create_logistic_when_create_payment | 5 | 11
| should_return_400_when_post_payment_fail | 3 | 2
| should_return_200_when_get_payment_success | 5 | 4
| should_return_200_when_get_logistic_success | 8 | 3
| should_return_201_when_post_confirmation_success | 10 | 18
| should_return_400_when_post_confirmation_fail | 3 | 1
| should_return_200_when_get_confirmation_success | 5 | 6
| total | 107 | 190

## InventoryService
| Task | Estimate | Real | Remarks
Backend | set up project | 5
| should_return_201_when_post_inventory_unloading_success | 10
| should_return_400_when_post_inventory_unloading_fail | 3
| should_return_200_when_get_inventory_unloadings_success | 8
| should_return_200_when_get_inventory_unloading_success | 8
| should_return_404_when_get_inventory_unloading_success | 3
| should_return_201_when_post_inventory_success | 10
| should_return_400_when_post_inventory_fail | 3
| should_return_200_when_get_inventory_success | 8
| should_call_product_service_when_get_inventory | 8
| should_return_201_when_post_store_success | 10
| should_return_400_when_post_store_fail | 3
| should_return_200_when_get_stores_success | 8
| should_return_200_when_get_store_success | 8
| should_return_404_when_get_store_fail | 3
| should_return_201_when_patch_store_success | 10
| should_return_400_when_patch_store_fail | 3
| total | 111

## ProductService
| Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_product_success | 10 | 13
| should_return_400_when_post_product_fail | 3 | 3
| should_return_200_when_get_products_success | 8 | 2
| should_return_200_when_get_product_success | 8 | 7
| should_return_404_when_get_product_fail | 3 | 3
| should_return_201_when_put_product_success | 10 | 6
| total | 47 | 35

## PriceService
| Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_price_success | 10 | 11
| should_return_400_when_post_price_success | 3 | 1
| should_return_200_when_get_price | 8 | 7 | ％3F路经不识别问题
| total | 26 | 20

## RefundService
| Task | Estimate | Real | Remarks
| set up project | 5 | 0
Backend | should_return_201_when_post_returnOrder_success | 10
| should_create_returnItems_when_create_returnOrder | 5
| should_call_order_service_when_create_returnOrder | 8
| should_return_200_when_get_returnOrders_success | 8
| should_return_200_when_get_returnOrder_success | 8
| should_return_404_when_get_returnOrder_success | 3
| should_return_201_when_post_refund_success | 10
| should_return_400_when_post_refund_fail | 3
| should_return_200_when_get_refund_success | 8
| should_return_201_when_post_comfirmation_success | 10
| should_return_400_when_post_comfirmation_fail | 3
| should_return_200_when_get_comfirmation_success | 8
| total | 89 | 0

## CartService
| Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_cart_success | 10 | 10
| should_create_cartItems_when_create_cart | 5 | 10
| should_call_price_service_when_create_cart | 8 | 14
| should_return_400_when_post_cart_fail | 3 | 3
| should_return_200_when_get_cart | 8
| should_return_201_when_put_cart_success | 10
| should_return_400_when_put_cart_fail | 3
| total | 52

## UserService
| Task | Estimate | Real | Remarks
Backend | set up project | 5
| should_return_201_when_post_user_success | 10
| should_return_400_when_post_user_fail | 3
| should_return_201_when_put_user_success | 10
| should_return_400_when_put_user_fail | 3
| should_return_200_when_get_user_success | 8
| should_return_404_when_get_user_fail | 3
| total | 42

## Docker
Task | Estimate | Real | Remarks
package all services | 10
add docker file to all services | 15
add service docker in docker-compose.yml | 15
add mysql docker in docker-compost.yml | 10
launch docker and build images | 30
debugging | 40
total | 120

## FunctionTest
Task | Estimate | Real | Remarks

## ConfigService
Task | Estimate | Real | Remarks

## RegisterService
Task | Estimate | Real | Remarks