## OrderService
OrderService | Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_order_success | 10 | 29 | 解决准备好模版中的bug
| should_cteate_orderItem_when_create_order | 5 | 32 | order嵌套item，mabatis批量插入数据库
| should_call_price_service_when_create_orderitem | 8 | 13 | 引入MockServer
| should_call_inventory_service_when_create_orderItem | 8 | 12 | Map<String,List<Map>>转json
| should_return_400_when_post_order_fail | 3 | 16 | 调用其他服务失败情况
| should_return_200_when_get_orders_success | 8 | 12
| should_return_200_when_get_order_success | 8 | 10
| shoule_return_404_when_get_order_fail | 3 | 1
| should_return_201_when_post_payment_success | 10 | 19 | Context问题
| should_create_logistic_when_create_payment | 5 | 11
| should_return_400_when_post_payment_fail | 3 | 2
| should_return_200_when_get_payment_success | 5 | 4
| should_return_200_when_get_logistic_success | 8 | 3
| should_return_201_when_post_confirmation_success | 10 | 18
| should_return_400_when_post_confirmation_fail | 3 | 1
| should_return_200_when_get_confirmation_success | 5 | 6
| total | 107 | 190
Frontend Lib | set up project | 5
| create order | 20
| get orders | 10
| get order | 10
| create payment | 20
| get payment | 15
| get logistic | 10
| create confirmation | 20
| get confirmation | 10
| total | 120

## InventoryService
InventoryService | Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_store_success | 10 | 13
| should_return_400_when_post_store_fail | 3 | 2
| should_return_200_when_get_stores_success | 8 | 2
| should_return_200_when_get_store_success | 8 | 8
| should_return_404_when_get_store_fail | 3 | 1
| should_return_201_when_put_store_success | 10 | 7
| should_return_400_when_put_store_fail | 3 | 1
| should_return_201_when_post_inventory_unloading_success | 10 | 15
| should_return_400_when_post_inventory_unloading_fail | 3 | 1
| should_return_200_when_get_inventory_unloadings_success | 8 | 3
| should_return_200_when_get_inventory_unloading_success | 8 | 4
| should_return_404_when_get_inventory_unloading_fail | 3 | 3
| should_return_201_when_post_inventory_success | 10 | 25 | inventory需要items
| should_return_400_when_post_inventory_fail | 3 | 1
| should_return_200_when_get_inventory_success | 8 | 4
| total | 103 | 91
Frontend Lib | create store
get stores
get store
udate store
create uploading
get unloadings
get unloading
create inventory
get inventory
total

## ProductService
ProductService | Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_product_success | 10 | 13
| should_return_400_when_post_product_fail | 3 | 3
| should_return_200_when_get_products_success | 8 | 2
| should_return_200_when_get_product_success | 8 | 7
| should_return_404_when_get_product_fail | 3 | 3
| should_return_201_when_put_product_success | 10 | 6
| total | 47 | 35
Frontend Lib | create product
get products
get product
update product
total

## PriceService
PriceService | Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_price_success | 10 | 11
| should_return_400_when_post_price_success | 3 | 1
| should_return_200_when_get_price | 8 | 7 | ％3F路经不识别问题
| total | 26 | 20
Frontend Lib | set up project | 5 | 1
| create price | 15 | 8
| get price | 10 | 14
| total | 30 | 23
Extra | 创建price时检查product id与user id是否相符合
total

## RefundService
RefundService | Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_returnOrder_success | 10 | 13
| should_create_returnItems_when_create_returnOrder | 5 | 8
| should_call_order_service_when_create_returnOrder | 8 | 13
| should_call_price_service_when_create_returnOrder | 8 | 14 | 验证和计算逻辑
| should_return_200_when_get_returnOrders_success | 8 | 6
| should_return_200_when_get_returnOrder_success | 8 | 4
| should_return_404_when_get_returnOrder_fail | 3 | 2
| should_return_201_when_post_refund_success | 10 | 16 | 重构returnOrderApi
| should_return_400_when_post_refund_fail | 3 | 1
| should_return_200_when_get_refund_success | 8 | 8
| should_return_201_when_post_confirmation_success | 10 | 10
| should_return_400_when_post_confirmation_fail | 3 | 8 | confirmation失败逻辑
| should_return_200_when_get_confirmation_success | 8 | 5
| total | 97 | 109
Frontend Lib | create returnOrder
get returnOrders
get returnOrder
create refund
get refund
create confirmation
get confirmation
total

## CartService
CartService | Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_cart_success | 10 | 10
| should_create_cartItems_when_create_cart | 5 | 10
| should_call_price_service_when_create_cart | 8 | 14
| should_return_400_when_post_cart_fail | 3 | 3
| should_return_200_when_get_cart | 8 | 11
| should_return_201_when_put_cart_success | 10 | 13
| should_return_400_when_put_cart_fail | 3 | 1
| total | 52 | 63
Frontend Lib | create cart
get cart
update cart
total

## UserService
UserService | Task | Estimate | Real | Remarks
Backend | set up project | 5 | 1
| should_return_201_when_post_user_success | 10 | 6
| should_return_400_when_post_user_fail | 3 | 1
| should_return_201_when_put_user_success | 10 | 4
| should_return_400_when_put_user_fail | 3 | 1
| should_return_200_when_get_user_success | 8 | 5
| should_return_404_when_get_user_fail | 3 | 1
| total | 42 | 19
Frontend Lib | set up project | 5 | 1
| create user | 20 | 35 | 调试发包请求
| update user | 10 | 5
| get user | 10 | 4
| total | 45 | 45

## Docker
Docker | Task | Estimate | Real | Remarks
| package all services | 10 | 28 | 解决migration问题，写 shell脚本
| add service docker in docker-compose.yml | 15 | 16 | 拉docker时间未记入
| add mysql docker in docker-compost.yml | 10 | 6 | 拉docker时间未记入
| add nginx | 15 | 14
| launch docker and debugging | 60 | 58
| total | 110 | 122

## Extra
Extra | Task | Estimate | Real | Remarks
| 写shell脚本解决docker启动顺序问题 | 120 | 125
| mysql docker数量由七个合为一个，使用不同数据库 | 120 | 75 | 性能问题
| 修复nginx location | 60 | 55
| total | 300 | 255

## total
Service |  | Estimate | Real | Remarks
OrderService | Backend | 107 | 190 | 第一个服务生疏
Frontend Lib
InventoryService | Backend | 103 | 91
Frontend Lib
ProductService | Backend | 47 | 35
Frontend Lib
PriceService | Backend | 26 | 20
| Frontend Lib | 30 | 23
RefundService | Backend | 97 | 109 | 退款、确认等逻辑验证
Frontend Lib
CartService | Backend | 52 | 63
Frontend Lib
UserService | Backend | 42 | 19
| Frontend Lib | 45 | 45
Docker |  | 110 | 122
Extra |  | 300 | 255
Total |  | 959 | 972